## Sheet 1
IMPLEMENTATION PLAN
Task | Description | Target Date
Finding Location | Identifying a suitable high traffic place | March 01 - 06
Space | Understanding the space needed for the business | March 07 - 10
Business Registration | Complete all the legal requirements for business resgistration | March 14 – 17
Rental Agreement | Talk with Mall management to finalize rental agreement | March 11-12
Framers Market | Advance booking and payment for the Farmers Market stall | March 13
Bank Account | For financial transactions, opening a business account | March 18-19
Obtain necessary permits | Food handling, health & safety license, Insurance | March 20-27
Pricing | Create the menu and establish final pricing. | March 28-29
Design and Print | Create and print promotional materials for business marketing | March 30-31
Supplier contracts. | Establish contact with local farmers and suppliers for steady supply | April 01-10
Purchase equipment | Blender, Juicers, Refrigerator and printer | April 11-13
Marketing | Getting the publicity through social media, distributing fliers. | April 15 - 31
Opening | Launch the business | May 01